## Slide 1
Planning and Estimation
https://flic.kr/p/hcgHcm

## Slide 2
Now you have a bunch of user stories, so what’s next?

## Slide 3: Iterative Development Process
Requirements
Planning
Analysis
Design
Implementation
Deployment
Testing
Evaluation
Initial Planning
We are here

## Slide 4
Choose USs for Iteration
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers
Get to Work!
Developer
Customer
Create USs
Requirements
USs
Check USs
Corrections/Clarifications
Fix USs
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities

## Slide 5
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Get to Work!
Developer
Customer
Fix USs
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers

## Slide 6: Estimating Time
http://xkcd.com/1658/

## Slide 7: Hofstadter's Law
It always takes longer than you expect, even when you take into account Hofstadter's Law.
— Douglas Hofstadter, Gödel, Escher, Bach

## Slide 8: Principles for Estimation
Principle: Past performance is the best indicator of future performance
  Approach: Track your outcomes; refine your estimates
Principle: Wisdom of the crowd
  Goal: Predict how events will unfold
    Think event planning
  Problem: Easy to miss something
  Solution: More brains = more opportunities to catch eventualities

## Slide 9: Principles for Estimation
Principle: Past performance is the best indicator of future performance
  Approach: Track your outcomes; refine your estimates
Principle: Wisdom of the crowd
  Goal: Predict how events will unfold
    Think event planning
  Problem: Easy to miss something
  Solution: More brains = more opportunities to catch eventualities
No past performance yet, so…

## Slide 10: Estimation with Planning Poker
Cards with units of work: 1, 3, 5, 8, 13, 20, 40
  Assume team can do 20 units in an iteration
For each US:
  Discuss work involved
  Flip cards
  Repeat until consensus
Efficiency in estimating is important
  Don’t expect your estimates to be super accurate

## Slide 11
Let’s watch this video to find out what planning poker is all about:
http://youtu.be/0FbnCWWg_NY

## Slide 12: More Estimation Principles
Engineers refine estimates; customers refine expectations
  Estimates are basis for customer’s cost assessment
Give honest estimates that customers can trust
  Don’t do this: https://youtu.be/t9SVhg6ZENw
Work at a sustainable pace
  No heroes, no all-nighters, no super-human feats
  Either you get the code done like a human being, or you don’t

## Slide 13
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Get to Work!
Developer
Customer
Fix USs
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers

## Slide 14: Principle: Customer sets priorities
Ensures alignment with customer goals
Helps customer feel in control
  Project isn’t going “off the rails”
Estimates help customer maximize cost-benefit

## Slide 15: Priority Numbering Scheme
Multiples of 10:
  10 - Highest priority
  20
  30
  40
  50
  … - Lowest priority
Non-multiples of 10 may be used if helpful

## Slide 16: So now you have…
Collection of user stories
  With estimates
  And customer priorities
What’s next?

## Slide 17
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Get to Work!
Developer
Customer
Fix USs
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers

## Slide 18: From USs to Tasks
Estimate
User Story

## Slide 19: Incremental Development Principle
Each task produces running code
  Unit tests count

## Slide 20: Task design strategy
Make tasks build upon one another
  First task makes subset of US work (e.g., partial form)
  Second task makes bit more work (e.g., add persistence)
  Etc…

## Slide 21: Next Steps
Part 1: Estimate USs
  Use Planning Poker
  Start designing
Part 2: Collect customer priorities
  Assign number each US
  Also note any corrections/clarifications
Part 3:
  Choose USs for Development Iteration 1
    3 weeks worth of work
  Fill out iteration plan with what each team member will do
    Everyone codes
    Tasks must be verifiable and executable
    Due by 9am on Mon