## Slide 1
Iteration Planning
https://flic.kr/p/hcgHcm

## Slide 2
Now you have a bunch of user stories with estimates, so what’s next?

## Slide 3
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers
Get to Work!
Developer
Customer
Fix USs

## Slide 4: Principle: Customer sets priorities
Ensures alignment with customer goals
Helps customer feel in control
  Project isn’t going “off the rails”
Estimates help customer maximize cost-benefit

## Slide 5: Priority Numbering Scheme
Multiples of 10:
  10 - Highest priority
  20
  30
  40
  50
  … - Lowest priority
Non-multiples of 10 may be used if helpful

## Slide 6: So now you have…
Collection of user stories
  With estimates
  And customer priorities
What’s next?

## Slide 7
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers
Get to Work!
Developer
Customer
Fix USs

## Slide 8: What’s next…
Choose subset of USs to implement this iteration
  Based on customer priorities
  Based on time constraints
Breakdown subset into tasks
  More detailed estimates
  May affect iteration plan
Assign people to tasks

## Slide 9: From USs to Tasks
Estimate
User Story

## Slide 10: Incremental Development Principle
Each task produces running code
  Unit tests count

## Slide 11: Task design strategy
Make tasks build upon one another
  First task makes subset of US work (e.g., partial form)
  Second task makes bit more work (e.g., add persistence)
  Etc…

## Slide 12: 2-Part Activity
Part 1: Collect customer priorities
  Assign number each US
  Also note any corrections/clarifications
Part 2:
  Choose USs for Development Iteration 1
    3 weeks worth of work
  Fill out iteration plan with what each team member will do
    Everyone codes
    Tasks must be verifiable and executable
    Due by start of next class!